## Sheet1
Column 1 | Column 2 | Column 3 | Column 4 | Column 5 | Column 6

## Sheet2
Tugas | Status | Pemilik | Tahap | Batas waktu | Catatan
| Belum dimulai |  | Sebelum acara
| Dalam proses |  | Hari ke-
| Diblokir |  | Setelah acara
Selesai

## Sheet3
Tugas | Prioritas | Pemilik | Status | Tanggal mulai | Tanggal akhir | Pencapaian | Hasil akhir | Catatan
| P0 |  | Belum dimulai
| P1 |  | Dalam proses
| P2 |  | Diblokir
| P3 |  | Selesai

## Sheet4
Konten | Jenis | Detail | Pemilik | Status | Tanggal postingan | File | Catatan
| Email |  |  | Baru
| Media sosial |  |  | Dalam proses
| TV |  |  | Dalam peninjauan
| Postingan blog |  |  | Dipublikasikan
| Semua |  |  | Ditangguhkan
Dijeda

## Sheet5
Fitur | Kategori | Status | Pemilik | Ukuran | Peluncuran | Catatan
| Kategori 1 | Belum dimulai |  | XS | Kuartal 1
| Kategori 2 | Dalam proses |  | S | Kuartal 2
| Kategori 3 | Diblokir |  | M | Kuartal 3
| Kategori 4 | Telah Diluncurkan |  | L | Kuartal 4
XL
XXL

## Sheet6
Pemohon | Tahap | Peran | Tim | Resume | Pewawancara | Skor | Catatan
| Diterima |  | Tim 1 |  |  | 0
| Wawancara |  | Tim 2 |  |  | 0
| Perlu keputusan |  | Tim 3 |  |  | 0
| Tidak diterima |  | Tim 4 |  |  | 0
0
0
0
0
0
0
0
0
0
0

## Sheet7
No | Task | Description | PIC (Person In Charge) | Tools | Task Process | Week 1 | Week 2 | Week 3 | Week 4 | Week 5 | Week 6 | Week 7 | Week 8 | Week 9 | Week 10 | Week 11 | Week 12 | Week 13 | Week 14 | Week 15 | Week 16
1.0 | Project Planning
2025-01-01 | Discussion | Team discussion to align project ideas | All |  | 100% | bar: Week 1
2025-02-01 | Project Agreement | Agreeing on project | All |  | 100% | bar: Week 2
2.0 | Data Gathering and Research
2025-01-02 | Preparing for Interview | Prepare questions and interview flow | All |  | 100% | bar: Week 7
2025-02-02 | Interview Result | Summarize and analyze interview findings | All |  | 100% | bar: Week 7
3.0 | Project Requirement
2025-01-03 | User Persona | Create user profiles | All | Canva | 100% | bar: Week 8
2025-02-03 | User Journey Map | Visualize user steps in using the app | All | Canva | 100% | bar: Week 8
2025-03-03 | User Emphaty Map | Show user feelings and thoughts | All | Canva | 100% | bar: Week 8
2025-04-03 | Wireframe | Draft basic layout and app flow | All | Figma and Canva | 100% | bar: Week 11
4.0 | Development
2025-01-04 | Journal | Writing Journal App Development |  | Word | 30%% | bar: Week 11
2025-02-04 | Quisionare | Create Quesionare to get user feedback |  | Google Form | 100%% | bar: Week 11
2025-03-04 | Artifact | Compiling Artifacts of Human Computer Interaction |  |  | 0%
2025-04-04 | Application Deisgn | Design app interface |  | Figma | 0%
2025-05-04 | Evaluation UI/UX | Define Evaluation Needs |  |  | 0%
5.0 | Exhibiton
2025-01-05 | Prepare Exhibition | Quality Control of Portis Project |  |  | 0%
2025-02-05 | Submit Exhibition | Submitting Portis to Taman Ismail Marzuki Exhibition |  |  | 0%